## Deliverables and Pymt Schedule
Appendix E, Deliverables and Payment Schedule
New Hampshire Department of Health and Human Services
Vendor Name:
Services: System of Care for Healthy Aging Planning and Reporting Consultation
Item | Activity / Document | Contract Section | Due Date* (specific date, or days/months from the contract effective date, estimated April 2024) | ESTIMATED Dates* (based on an estimated effective date of April 10, 2024) | Price**
1 | Conduct project kick-off meeting. | 2.1.2.1. | Within fifteen (15) days of the contract effective date. | Wed 5/1/24
2 | Project Management, including project status reports twice per month. Due date is for first project status report. | 2.1.2.2., 2.1.7.1. | Within fifteen (15) days of the kick-off meeting. | Wed 5/22/24
3 | Submit plan outline to the Department: System of Care for Healthy Aging Plan. | 2.1.4.1. | Within three (3) months of the contract effective date. | Wed 7/10/24
4 | Stakeholder listening sessions (minimum of two (2)) and stakeholder focus groups (minimum of two (2)). | 2.1.3.1.1. | Within four (4) months of the contract effective date. | Mon 8/12/24
5 | Submit plan draft to the Department: System of Care for Healthy Aging Plan. | 2.1.4.2.3. | Within five (5) months of the contract effective date. | Tues 9/10/24
6 | Review draft during in-person meeting with the Department. | 2.1.4.2.4. | Within two (2) weeks of draft submittal described in Item 5. | Tues 9/24/24
7 | Submit SFY 2024 report to the Department. | 2.1.7.2. | On or before October 1, 2024. | Tues 10/1/24
8 | Release updated draft to the public: System of Care for Healthy Aging Plan. | 2.1.4.2.5. | Within two (2) weeks of the meeting described in Item 6. | Tues 10/8
9 | Review public input during in-person meeting with the Department. | 2.1.4.2.6. | Within two (2) weeks of the draft release described in Item 8. | Tues 10/22
10 | Submit final plan draft to the Department: System of Care for Healthy Aging Plan. | 2.1.4.3.1. | Within one (1) week of the meeting described in Item 9. | Tues 10/29
11 | Distribute System of Care for Healthy Aging Plan, as directed by the Department. | 2.1.4.3.2. | On or after submittal of the final draft described in Item 10. | Tues 10/29
12 | Submit content to be used to inform creation of the public-facing online dashboard. | 2.1.3.1.3. | On or before May 30, 2025. | Fri 5/30/25
13 | Submit draft SFY 2025 report to the Department. | 2.1.7.3. | On or before June 30, 2025. | Mon 6/30/25
| Total |  |  |  | 0
Total should equal $200,000
*Dates are subject to change. **The selected Applicant will complete price for each deliverable for Department approval.
RFA-2024-DLTSS-01-SYSTE